## Gantchart
GANTT CHART Mini Project | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE: Leave Management System | [6 empty] | DEPARTMENT : Information Technology Engineering
PROJECT GUIDE: Prof. Sushmita Das | [6 empty] | DATE: 10-04-2022
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PERCENTAGE OF TASK COMPLETE | PHASE ONE | [24 empty] | PHASE TWO
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
WEEK 1 | Group formation and Topic finalization. Identifying the scope and objectives of the Mini Project | Shreya Mahajan, Saniya Dutta, Anish Bhosale, Kunal Palande | 26/01/2022 | 29/01/2022 | 1 | 100% | bar: WEEK 1 F to WEEK 2 F
WEEK 2 | Identifying the technology stack and functionalities of the Mini Project | Shreya Mahajan, Saniya Dutta | 2022-05-02 | 2022-10-02 | 1 | 100% | bar: WEEK 2 M to WEEK 2 F
WEEK 3 | Discussing the project topic with the help of paper prototype. | Anish Bhosale, Kunal Palande | 15/02/2022 | 20/02/2022 | 1 | 100% | bar: WEEK 2 M to WEEK 3 W
WEEK 4 | Presentation I | Shreya Mahajan, Saniya Dutta, Anish Bhosale, Kunal Palande | 16/03/2022 | 16/03/2022 | 0 | 100% | bar: WEEK 2 M to WEEK 3 R
2 | Project Design and Implementation
WEEK 5 | Designing the Graphical User Interface(GUI) | Shreya Mahajan, Saniya Dutta, Anish Bhosale, Kunal Palande | 2022-05-02 | 2022-05-03 | 4 | 100% | bar: WEEK 2 M to WEEK 3 R
WEEK 6 | Database Design | Shreya Mahajan, Saniya Dutta, Anish Bhosale, Kunal Palande | 2022-08-03 | 18/03/2022 | 2 | 100% | bar: WEEK 2 M to WEEK 2 F; WEEK 4 M to WEEK 4 R
WEEK 7 | Database Connectivity with front end | Shreya Mahajan, Anish Bhosale | 20/03/2022 | 30/03/2022 | 2 | 100% | bar: WEEK 2 M to WEEK 2 F; WEEK 4 F to WEEK 5 F
WEEK 8 | Results and Report Writing | Saniya Dutta, Kunal Palande | 2022-01-04 | 2022-08-04 | 1 | 100% | bar: WEEK 2 M to WEEK 2 F; WEEK 5 M to WEEK 8 F
WEEK 9 | Presentation II | Shreya Mahajan, Saniya Dutta, Anish Bhosale, Kunal Palande | 2022-12-04 | 2022-12-04 | 0 | 100% | bar: WEEK 2 M to WEEK 2 F; WEEK 8 M to WEEK 9 F
2022-03-08